## Reskell Kanban JIRA Board 524c4
Name | Assigned To | Date | Completion Date | Epic | Estimate | Remaining | Sprint | Status | Story
SPRINT 1
Options Config File | Malcome |  |  | Main Menu |  |  | 0 | Backlog
3rd Person Camera Control | Lorenzo | October 25, 2021 → October 28, 2021 | 2021-10-28 | Mechanics | 5 | 19 | 1 | Completed | As a Player, I want to have a comfortable camera spacing/preset, so that I can see the beautiful Chad I created at different angles.
Character Appearance | Lorenzo | October 31, 2021 → November 3, 2021 | 2021-11-03 | Characters | 5 | 14 | 1 | Completed | As Player, I want to have a character with clothes and hair, so that I can not freak out
Skybox | Lorenzo | October 31, 2021 → November 3, 2021 | 2021-11-03 | Environment | 3 | 11 | 1 | Completed
Background music | Lorenzo | October 31, 2021 → November 4, 2021 | 2021-11-04 | Audio | 3 | 8 | 1 | Completed
Rain and Environmental Effects | Lorenzo | October 30, 2021 → November 5, 2021 | 2021-11-05 | Effects | 8 | 0 | 1 | Completed
Load | Malcome |  |  | Main Menu |  |  | 1 | Not started | As Player, I want to access press Load in the main menu, so that I can load my save files.
Access Main Menu | Malcome |  |  | Main Menu |  |  | 1 | Completed | As Player, I want to press New Game in the main menu, so that I can play.
Options | Malcome |  |  | Main Menu |  |  | 1 | Completed | As Player, I want to access press Options in the main menu, so that I can change settings.
Exit Game | Malcome |  |  | Main Menu |  |  | 1 | In progress | As Player, I want to access press Exit Game in the main menu, so that I can exit.
New Game | Malcome |  |  | Main Menu |  |  | 1 | Completed | As Player, I want to press New Game in the main menu, so that I can play.
Save | Malcome |  |  | Main Menu |  |  | 1 | In progress | As Player, I want to access press Save Game in the main menu, so that I can save my progress.
Save File | Malcome |  |  | Main Menu |  |  | 1 | In progress | As Player, I want to be able to save my progress, so that I can resume later on
SPRINT 2
Get doors working | Lorenzo | November 22, 2021 → November 24, 2021 | 2021-11-24 | Environment | 8 | 55 | 2 | Completed
Fix asset flickering issues | Lorenzo | November 22, 2021 → November 24, 2021 | 2021-11-24 | Environment | 8 | 47 | 2 | Completed
Work on making the lights flicker | Lorenzo | December 1, 2021 → December 2, 2021 | 2021-12-02 | Effects | 13 | 47 | 2 | In progress
Rework Ocean Base | Lorenzo | November 22, 2021 → December 2, 2021 | 2021-12-02 | Environment | 13 | 47 | 2 | In progress
Environmental Damage Effects | Lorenzo |  | 2021-12-02 | Effects | 13 | 47 | 2 | Not started
Enemy Design | Lorenzo, Malcome | December 1, 2021 → December 2, 2021 | 2021-12-02 | Mechanics | 8 | 47 | 2 | In progress
2021-11-22 | 63 | 63
2021-11-23 | 63
2021-11-24 | 55
2021-11-24 | 47
2021-11-25 | 47
2021-11-26 | 47
2021-11-27 | 47
2021-11-28 | 47
2021-11-29 | 47
2021-11-30 | 47
2021-12-01 | 47
2021-12-02 | 47 | 0